## Gantt Chart
GANTT CHART
PROJECT TITLE |  | Poké Mart POS |  |  |  |  | ORGANIZATION NAME |  | SUNY New Paltz
PROJECT ADVISOR |  | Anthony Denizard |  |  |  |  | DATE |  | 2022-01-24
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE
[7 empty] | W1 2/7/2022 | W2 2/14/2022 |  | W3 2/21/2022 | W4 2/28/2022 | W5 3/7/2022 | W6 3/14/2022 | W7 3/21/2022 | W8 3/28/2022 | W9 4/4/2022 | W10 4/11/2022 | W11 4/18/2022 | W12 4/25/2022 | W13 5/2/2022 | W14 5/9/2022
1 | Project Conception and Initiation
1.1 | Setting up Github | Matt | 2022-02-02 | 2022-02-10 | 8 | 50%
1.2 | Setting up Webex Account | All | 2022-02-03 | 2022-02-03 | 0 | 100%
1.3 | Setting up XAMPP | All | 2022-02-07 | 2022-02-10 | 3 | 0%
1.4 | Assigning Group Leader | All | 2022-01-31 | 2022-01-31 | 0 | 100%
1.5 | Setting up Webex Meeting Room | Matt | 2022-02-03 | 2022-02-03 | 0 | 100%
1.6 | Project Proposal | Matt | 2022-02-03 | 2022-02-03 | 0 | 100%
1.7 | Flowcharts (Visio) | All | 2022-02-07 | 2022-02-10 | 3 | 0%
2 | Design
2.1 | Website Layout | Jayce |  |  | 0 | 0%
2.2 | Music | Tyquan |  |  | 0 | 0%
2.3 | UI Elements (shopping cart, etc.) | Jayce |  |  | 0 | 0%
2.4 | Purchase Acknowledgement | Maranda |  |  | 0 | 0%
2.5 | Color Schemes | Jayce |  |  | 0 | 0%
2.6 | Accessibility | Tyquan |  |  | 0 | 0%
2.7 |  |  |  |  | 0
2.8 |  |  |  |  | 0
2.9 |  |  |  |  | 0
2.1 |  |  |  |  | 0
2.11 |  |  |  |  | 0
2.12 |  |  |  |  | 0
3 | Data storage
3.1 | Inventory | Anabel |  |  | 0 | 0%
3.2 | Vendors | Maranda |  |  | 0 | 0%
3.3 | Transactions | Jayce |  |  | 0 | 0%
3.4 | Customer/Client Information | Analiza |  |  | 0 | 0%
3.5 | Orders/Sales | Anabel |  |  | 0 | 0%
3.6 | Employees | Matt |  |  | 0 | 0%
3.7 | Z-Report | Maranda |  |  | 0 | 0%
3.8 | Security Systems | Matt |  |  | 0 | 0%
3.9 | Payroll | Analiza |  |  | 0 | 0%
3.1 | Profit/Loss Reports | Jayce |  |  | 0 | 0%
3.11 | Report Grouping | Anabel |  |  | 0 | 0%
3.12 | Session Handling | Tyquan |  |  | 0 | 0%